## Sheet1
Risk | Description | Prob of Occur | Damage | Mitigation strategy | Person in charge | Risk factor
External loss of Server environment | Loss of Server due to missing security mechanism (Passwords, Root User, …) | 8 | 10 | Using strong passwords and transfering them encripted. Make Backups of the Software | Konrad | 80
Bad Riskmanagement | Missing out potential risks or not enforcing the team to tackle the problems | 8 | 7 | Periodical Riskrefinement | Jan | 56
Bad Documentation | Waste of Time and worse Grading. Frustration and bad overview | 9 | 5 | Periodical Documentation Reviews | Konrad | 45
Internal loss of Server environment | Loss of Server due to missing security mechanism (Bad Branchin strategy, Password changes without saving it) | 3 | 10 | Advance Git-Branching Strategy. Make Backups on the Software | Jan | 30
Inconsistent/Bad Executed Architecture | Bad Codequality -> worse grades. Inconsistent Codestyle -> hard to understand | 7 | 3 | Periodical Codereviews | Rico | 21
Temporary lack of Workforce | Members cant continue to work (Temporary illness) | 5 | 3 | minor reduction of code-quality / functionality. More workload for other members | Rico | 15
Shrinking motivation | Teammembers motiviation shrinks | 10 | 1 | See the task abstreact as a rational necessary task for completion | Jan | 10
Permanent lack of Workforce | Members cant continue to work (Quitting Course) | 1 | 7 | greater reduction of code-quality / functionality | Rico | 7